## Overview
Streamining the patient registration experience at Oceanview Hospital
What? | Purpose: | To develop a new process for patient registration in emergency.
Why? | Emergency Room Physicians are finding that the patients they see are wearing at least 5 wristbands from the hospital, all with the same information on them. This seems inefficient and unnecessary.
When? | Project Start: | 2022-01-01
| Project Finish: | 2022-06-01
Who? | Project Team: | Dr. M. Geller-Bing | Project Lead | WG member | m.gellerbing@oceanview.ca
|  | C. Bing | Project Manager | WG member | c.bing@gmail.com
|  | Dr. J. Tribiani | ER physician | WG member | j.tribiani@oceanview.ca
|  | Dr. P. Buffay | ER physician | WG member | p.buffay@oceanview.ca
|  | X. Gunther | Site Administrator | WG member | x.gunther@oceanview.ca
|  | R. Green | ER Manager | WG member | r.green@oceanview.ca
|  | R. Geller | Patient partner |  | pivot@gmail.com
How? | 1. Determine existing process happening for patient registration.
2. Discuss potential ways to streamine registration.
3. Trial best possible solution.
4. Measure effectiveness of trial. Iterate as necessary.
How will we know the project is successful?
Physician experience
Triage nurse experience
Patient experience
Number of wristbands before and after
ER manager observations

## Details
Streaminling the patient registration experience at Oceanview Hospital
Activity/Milestones | Details | Responsible | Actions | Status | Timeframe | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
1. Determine existing process happening for patient registration.
| Speak with ER manager, observe in ER | Monica | Monica set up meeting with Rachel | Complete | 2022-01-01 | bar: Jan
| Interview Patient Partner | Chandler | Chandler set up meeting with Ross | In Progress | 2022-01-01 | bar: Jan
| Meet to compare notes | Monica, Chandler | Touch base when done, set up coffee meeting | Not Started | 2022-01-01 | bar: Jan
2. Discuss potential ways to streamine registration.
| WG Meeting 1 - Review problem, review results of interviews | WG | Chandler send out doodle poll Jan for Feb meeting | Not Started | 2022-02-01 | bar: Feb
| WG Meeting 2 - Brainstorm solutions, prioritize | WG | Chandler send out doodle poll Feb for Mar meeting | Not Started | 2022-03-01 | bar: Mar
3. Trial best possible solution.
| Meet with Rachel to discuss trial logistics | Monica | Monica set up meeting with Rachel | Not Started | 2022-04-01 | bar: Apr
| Support Rachel to implement | Monica, Joey, Phoebe | Huddles every Monday | Not Started | 2022-04-01 | bar: Apr
4. Measure effectiveness of trial. Iterate as necessary.
| Measure pre-implementation results | Chandler | Chandler set up time to observe in ER | Not Started | 2022-03-01 | bar: Mar
| Measure post-implementation results | Chandler | Chandler set up time to observe in ER | Not Started | 2022-05-01 | bar: May
| WG Meeting 3 - Present results of trial, make decisions on next steps | WG | Chandler send out doodle poll May for Jun meeting | Not Started | 2022-06-01 | bar: Jun
Project Administration
| Develop project plan | Monica, Chandler |  | In Progress | 2022-12-01 | bar: Dec
| Submit Q1 report to MSA per email | Chandler |  | Not Started | 2022-03-01 | bar: Mar
| Submit Q2 report to MSA per email | Chandler |  | Not Started | 2022-06-01 | bar: Jun
| Final report to MSA | Monica, Chandler |  | Not Started | 2022-07-01 | bar: Jul

## Gantt
Details | Responsible | Timeframe | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
Develop project plan | Monica, Chandler | 2021-12-01 | Dec: 4 hours
Speak with ER manager, observe in ER | Monica | 2022-01-01 | Jan: 4 hours
Interview Patient Partner | Chandler | 2022-01-01 | Jan: 1 hour
Meet to compare notes | Monica, Chandler | 2022-01-01 | Jan: 1 hour
WG Meeting 1 - Review problem, review results of interviews | WG | 2022-02-01 | Feb: 1.5 hours
WG Meeting 2 - Brainstorm solutions, prioritize | WG | 2022-03-01 | Mar: 1.5 hours
Measure pre-implementation results | Chandler | 2022-03-01 | Mar: 2 hours
Submit Q1 report to MSA per email | Chandler | 2022-03-01 | Mar: 1 hour
Meet with Rachel to discuss trial logistics | Monica | 2022-04-01 | Apr: 1 hour
Support Rachel to implement | Monica, Joey, Phoebe | 2022-04-01 | Apr: 2 hours
Measure post-implementation results | Chandler | 2022-05-01 | May: 2 hours
WG Meeting 3 - Present results of trial, make decisions on next steps | WG | 2022-06-01 | Jun: 1.5 hours
Submit Q2 report to MSA per email | Chandler | 2022-06-01 | Jun: 1 hour
Final report to MSA | Monica, Chandler | 2022-07-01 | Jul: 1 hour